## Ark1
Loftus Frukt Og Saft Gantt Chart
PROJECT: Loftus Frukt og Saft Website
PROJECT MANAGER: Hermon Tesfay |  |  |  |  | SEPTEMBER | [27 empty] | OKTOBER | [27 empty] | NOVEMBER
Project Timelapse |  |  |  |  | PLANNING PHASE | [27 empty] | DESIGN PHASE | [27 empty] | BUILDING/LAUNCH PHASE
| Date Start:01.09.2020 | Date End: 22.11.2020 | Duration: 12 Weeks |  | UKE 1 | [6 empty] | UKE 2 | [6 empty] | UKE 3 | [6 empty] | UKE 4 | [6 empty] | UKE 5 | [6 empty] | UKE 6 | [6 empty] | UKE 7 | [6 empty] | UKE 8 | [6 empty] | UKE 9 | [6 empty] | UKE 10 | [6 empty] | UKE 11 | [6 empty] | UKE 12
Team Members |  |  |  |  | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn | man | tir | ons | tor | fre | lør | søn
Project Manager: Hermon Tesfay | Frontend-Devoloper: Abimbola Adisa | Senior Devoloper: Afia Akua | Copywriter: Aaamina Abina | Photographer: Hakim Abedemi | 2020-09-01 | 2020-09-02 | 2020-09-03 | 2020-09-04 | 2020-09-05 | 2020-09-06 | 2020-09-07 | 2020-09-08 | 2020-09-09 | 2020-09-10 | 2020-09-11 | 2020-09-12 | 2020-09-13 | 2020-09-14 | 2020-09-15 | 2020-09-16 | 2020-09-17 | 2020-09-18 | 2020-09-19 | 2020-09-20 | 2020-09-21 | 2020-09-22 | 2020-09-23 | 2020-09-24 | 2020-09-25 | 2020-09-26 | 2020-09-27 | 2020-09-28 | 2020-09-29 | 2020-09-30 | 2020-10-01 | 2020-10-02 | 2020-10-03 | 2020-10-04 | 2020-10-05 | 2020-10-06 | 2020-10-07 | 2020-10-08 | 2020-10-09 | 2020-10-10 | 2020-10-11 | 2020-10-12 | 2020-10-13 | 2020-10-14 | 2020-10-15 | 2020-10-16 | 2020-10-17 | 2020-10-18 | 2020-10-19 | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-24 | 2020-10-25 | 2020-10-26 | 2020-10-27 | 2020-10-28 | 2020-10-29 | 2020-10-30 | 2020-10-31 | 2020-11-01 | 2020-11-02 | 2020-11-03 | 2020-11-04 | 2020-11-05 | 2020-11-06 | 2020-11-07 | 2020-11-08 | 2020-11-09 | 2020-11-10 | 2020-11-11 | 2020-11-12 | 2020-11-13 | 2020-11-14 | 2020-11-15 | 2020-11-16 | 2020-11-17 | 2020-11-18 | 2020-11-19 | 2020-11-20 | 2020-11-21 | 2020-11-22
TEAM MEMBER | TASK DESCRIPTION | START DATE | END DATE | DURATION | 2020-09-01: GOAL:Planning Content, Identify Goal, Strategy & Research. | GOAL: Create Site Structure, Create Content, Photos. | [27 empty] | GOAL: Build Mobile Responsiv Site, Check Usability, Launch Site.
Project Manager: Hermon Tesfay | Plan Project & Keep everybody informed. | 2020-09-01 | 2020-11-22 | 12 Weeks | 2020-09-01: MEETING
Frontend-Devoloper: Abimbola Adisa | Build structuct and construct site | 2020-09-29 | 2020-11-22 | 8 Weeks | 2020-09-08: Research
Senior Devoloper: Afia Akua | Optimize site & Support | 2020-09-01 | 2020-11-22 | 12 Weeks | 2020-09-08: Research
Copywriter: Aaamina Abina | Create marketing advertisement | 2020-10-11 | 2020-09-01 | 2 Weeks | 2020-09-08: Research
Photographer: Hakim Abedemi | Photography For Site | 2020-09-01 | 2020-09-01 | 6 Weeks | bar: 2020-09-01 to 2020-09-03
Senior Devoloper: Afia Akua |  |  |  |  | 2020-09-15: Plan Content
Project Manager: Hermon Tesfay | bar: 2020-09-15 to 2020-09-20
Copywriter: Aaamina Abina | bar: 2020-09-15 to 2020-09-20
Frontend-Devoloper: Abimbola Adisa |  |  |  |  | 2020-09-21: SITE MOCK UP
Senior Devoloper: Afia Akua | bar: 2020-09-21 to 2020-09-26
Frontend-Devoloper: Abimbola Adisa | [32 empty] | SITE STRUCTURE
Photographer: Hakim Abedemi | [44 empty] | PHOTOSHOT PRODUCTION AND PRODUCTS | [6 empty] | PHOTOSHOOT EMPLOYEES
Create Text Content
Copywriter: Aaamina Abina
Senior Devoloper: Afia Akua
Create StyleTile
Project Manager: Hermon Tesfay | [56 empty] | MEETING(Client)
Frontend-Devoloper: Abimbola Adisa
Senior Devoloper: Afia Akua
Frontend-Devoloper: Abimbola Adisa
Frontend-Devoloper: Abimbola Adisa | [60 empty] | CODING BUILDING SITE
Frontend-Devoloper: Abimbola Adisa | [60 empty] | CREATE WIREFRAME
Senior Devoloper: Afia Akua | [74 empty] | USABILITY TESTING
Frontend-Devoloper: Abimbola Adisa
Frontend-Devoloper: Abimbola Adisa | [81 empty] | VALIDATE
Senior Devoloper: Afia Akua
Project Manager: Hermon Tesfay | [85 empty] | LAUNCH
Frontend-Devoloper: Abimbola Adisa
Senior Devoloper: Afia Akua